## Homekey Timeline
HCD - Homekey Timeline Template | [6 empty] | Week of:
Subject | Objective | Description | Start Date | Finish Date | Note | Data/Information Source(s) | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02
1
Requirements | Standard Agreement | Execution of Standard Agreement | 2020-09-15 | 2020-09-30 | xx
| Site Control | Letter of Intent and Exclusive Negotiating Agreement | 2020-07-29 | 2020-08-13 | xx
| Identifying Development Team | Eden Housing | 2020-08-03 | 2020-08-13 | xx
| Appraisal Document | Appraisal of Property - Semple Appraisals, Inc | 2020-09-15 | 2020-10-12 | xx
| Physical Needs Assessment | Contract Providers TBD | 2020-09-15 | 2020-10-12 | xx
| Accessibility and Non-Discrimination Statement | Submitted with Homekey Application | 2020-08-03 | 2020-08-10 | xx
| Preliminary commitment for Title Insurance | Cal Land Title | 2020-08-14 | 2020-09-04 | xx
| Liability Insurance Coverage | County of Marin is Self Insured and will provide a statement to that effect. | 2020-08-13 | 2020-08-21 | xx
| Applicant Compliance Certification | Submitted with Homekey Application | 2020-08-03 | 2020-08-10 | xx
| Certification of Occupancy | COO review and issuance | 2020-11-01 | 2020-11-30 | xx
2
Entitlements | Land use approval | Leverage AB83 preemption | 2020-08-13 | 2020-11-01 | xx
| Entitling jurisdicton support | Work with local jurisdictions to ensure political and community support for project | 2020-08-13 | 2020-11-01 | xx
| Not applicable | Not applicable | N/A | N/A | xx
3
Permits | Planning Permits | Application of all proposed project activities. Ministerial Review and Approval due to AB83 streamlining. Per AB83, project is deemed consistent with and in conformity with local planning and zoning requirements. | 2020-08-13 | 2020-11-30 | xx
| Building Plan Review | Concurrent building plan review | 2020-08-13 | 2020-11-01 | xx
| Building Permits | Building Permit Review, Inspections, and Finalizing for COO issuance | 2020-11-01 | 2020-11-30 | xx
4
Environmental Clearance | Site Assessment | Phase 1 Environmental Assessment will be part of Due Diligence Reports | 2020-09-15 | 2020-10-12 | xx
| Submitting Documents | CEQA Statutory Exemption, Notice of Exemption will be prepared and filed by Marin County Community Development Agency with the State Clearinghouse. | 2020-10-20 | 2020-11-01 | xx
| CEQA Clearance (even if using exemption the applicant must document the exemption) | Notice of Exemption will be prepared and filed by Marin County Community Development Agency and be stated in Resolution of Intention to Purchase | 2020-10-20 | 2020-11-01 | xx
| NEPA Clearance (if using local federal funding awards to support proposed activities) | Not Applicable | N/A | N/A | xx
5
Board or Governing Body Approval | Authorizing Resolution | Marin County Board of Supervisors authorization to apply for grant. | 2020-08-03 | 2020-08-11 | xx
| Resolution of Intention to Purchase Real Property and CEQA Findings | Marin County Board of Supervisors | 2020-09-16 | 2020-10-20 | xx
| Approval of Purchase and Sale Agreement and Funding Allocation | Marin County Board of Supervisors | 2020-10-20 | 2020-11-10
6
Closing Process | Closing Date | Close of Escrow through Cal Land Title will be coordinated as soon as feasible | 2020-11-10 | 2020-12-30 | xx
Note:
Applicants are required to provide answers to all lines above, even if the response is “Not Applicable.”
Applicants should include all key milestones (tracked for the proposed project) to aide in the partnership between the Department and the applicant.
Applicants can add other items as needed to clarify objectives and the implementation process.